## Cover Page
<Project Name>
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog <Goal Management System> Project ID: <DE26GNJFSA001/pod_003> C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | User Login | All | Users authenticate with email and password to access the system | Valid credentials grant access. Invalid credentials show error. Role-based dashboard displayed | Sprint-1 | 5
US_2 | Role-Based Access | All | System restricts features based on user role (EMPLOYEE, MANAGER, ADMIN) | Admin sees all features - Manager sees Team features - Employee sees personal features | Sprint-1 | 8
US_3 | User Management | Admin | Admin can create, view, update, and delete user accounts | Create new users with roles - View all users list - Update user details - Deactivate users | Sprint-2 | 13
US_4 | System Analytics | Admin | Admin can view system-wide analytics and reports | View total plans count - View user activity metrics - Export reports | Sprint-3 | 8
US_5 | Plan Oversight | Admin | Admin can view and manage all plans in the system | Access all user plans - Modify any plan - Delete any plan | Sprint-2 | 5
US_6 | Team Plan Creation | Manager | Managers can create plans for team members | Select team member<br>- Create plan with details<br>- Set priority levels | Sprint-1 | 5
US_7 | Team Plan Review | Employee | Managers can view and update team member plans. | View all team plans - Update plan status - Add comments to plans | Sprint-2 | 5
US_8 | Milestone Approval | Manager | Managers can review and approve team milestones | View pending milestones - Approve/reject milestones - Set milestone completion | Sprint-2 | 13
US_9 | Personal Plan Creation | Employee | Employees can create their own plans | Create plan with title/description - Set start/end dates - Define priority level | Sprint-1 | 5
US_10 | Milestone Management | Employee | Employees can create and track milestones for their plans | Add milestones to plans - Update completion percentage - Set milestone status | Sprint-1 | 8
US_11 | Plan Updates | Employee | Employees can update their plan details and status | Modify plan description - Update plan status - Adjust dates | Sprint-1 | 3
US_12 | Comment Collaboration | Employee | Employees can add comments to plans for collaboration | Add text comments - View comment history - Receive notifications | Sprint 2 | 5

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
| 0 | 100 | 0 | 100% | 0 | 0
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000